## Q1 network
|  |  | 4 | 2 | 12 |  |  |  | 14 | 7 | 18
|  |  | 2 |  | 2 |  |  |  | 0 |  | 0
|  |  | 6 | 8 | 14 |  |  |  | 14 | 4 | 18
0 | 1 | 4 | 4 | 3 | 10 | 10 | 5 | 14 |  |  |  | 18 | 8 | 22
0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 |  | 0
0 | 4 | 4 | 4 | 6 | 10 | 10 | 4 | 14 |  |  |  | 18 | 4 | 22
|  |  | 4 | 4 | 8 | 8 | 6 | 16
|  |  | 2 |  | 2 | 2 |  | 2
|  |  | 6 | 4 | 10 | 10 | 8 | 18
[9 empty] | ES | ID | EF
[9 empty] | LS | DUR | LF

## Q1 PV plan
Schedule Information | [5 empty] | Baseline PV ($00)
Activity / Work Package | Duration | Earliest Start | Latest Finish | Slack | Total Planned Value ($00) | Planned Value up to the end of the Time period below
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22
1 | 4 | 0 | 4 | 0 | 8 | Planned Value up to the end of the Time period below 2: 4; Planned Value up to the end of the Time period below 4: 4
2 | 8 | 4 | 14 | 2 | 40 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 10; Planned Value up to the end of the Time period below 10: 10; Planned Value up to the end of the Time period below 12: 10
3 | 6 | 4 | 10 | 0 | 30 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 15; Planned Value up to the end of the Time period below 10: 5
4 | 4 | 4 | 10 | 2 | 20 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 10
5 | 4 | 10 | 14 | 0 | 40 | Planned Value up to the end of the Time period below 12: 20; Planned Value up to the end of the Time period below 14: 20
6 | 8 | 8 | 18 | 2 | 60 | Planned Value up to the end of the Time period below 10: 20; Planned Value up to the end of the Time period below 12: 20; Planned Value up to the end of the Time period below 14: 10; Planned Value up to the end of the Time period below 16: 10
7 | 4 | 14 | 18 | 0 | 20 | Planned Value up to the end of the Time period below 16: 10; Planned Value up to the end of the Time period below 18: 10
8 | 4 | 18 | 22 | 0 | 30 | Planned Value up to the end of the Time period below 20: 20; Planned Value up to the end of the Time period below 22: 10
Total PV by period | [5 empty] | 4 | 4 | 30 | 35 | 35 | 50 | 30 | 20 | 10 | 20 | 10
Cummulative PV by period | [5 empty] | 4 | 8 | 38 | 73 | 108 | 158 | 188 | 208 | 218 | 238 | 248

## Q1 status report
Status Report: Ending Period 2
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 50 | 4 | 4 | 4 | 0 | 0
Cumulative totals |  | 4 | 4 | 4 | 0 | 0
Status Report: Ending Period 4
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0
Cumulative totals |  | 8 | 10 | 8 | -2 | 0
Status Report: Ending Period 6
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0
2 | 25 | 10 | 15 | 10 | -5 | 0
3 | 33 | 9.9 | 12 | 10 | -2.1 | -0.1
4 | 0 | 0 | 0 | 10 | 0 | -10
Cumulative totals |  | 27.9 | 37 | 38 | -9.1 | -10.1
Status Report: Ending Period 8
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0
2 | 30 | 12 | 20 | 20 | -8 | -8
3 | 60 | 18 | 25 | 25 | -7 | -7
4 | 0 | 0 | 0 | 20 | 0 | -20
Cumulative totals |  | 38 | 55 | 73 | -17 | -35
Status Report: Ending Period 10
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0
2 | 60 | 24 | 30 | 30 | -6 | -6
3 | 100 | 30 | 40 | 30 | -10 | 0
4 | 50 | 10 | 20 | 20 | -10 | -10
5 | 0 | 0 | 0 | 0 | 0 | 0
6 | 30 | 18 | 24 | 20 | -6 | -2
Cumulative totals |  | 90 | 124 | 108 | -34 | -18
Status Report: Ending Period 12
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0
2 | 100 | 40 | 50 | 40 | -10 | 0
3 | 100 | 30 | 40 | 30 | -10 | 0
4 | 100 | 20 | 40 | 20 | -20 | 0
5 | 50 | 20 | 30 | 20 | -10 | 0
6 | 50 | 30 | 40 | 40 | -10 | -10
Cumulative totals |  | 148 | 210 | 158 | -62 | -10

## Q1 indices table
Period | SPI | CPI | PCIB
2 | 1 | 1 | 1.61% | SPI = EV/PV
4 | 1 | 0.8 | 3.23% | CPI = EV/AC
6 | 0.73 | 0.75 | 11.25% | PCIB = EV/BAC
8 | 0.52 | 0.69 | 15.32%
10 | 0.83 | 0.73 | 36.29%
12 | 0.94 | 0.7 | 59.68%

## Q1 summary graph
Period | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22
($00) PV | 4 | 8 | 38 | 73 | 108 | 158 | 188 | 208 | 218 | 238 | 248
AC | 4 | 10 | 37 | 55 | 124 | 210
EV | 4 | 8 | 27.9 | 38 | 90 | 148
SPI | 1 | 1 | 0.73 | 0.52 | 0.83 | 0.94
PCI | 1 | 0.8 | 0.75 | 0.69 | 0.73 | 0.7
PCIB | 1.61% | 3.23% | 11.25% | 15.32% | 36.29% | 59.68%

## Q2 Do your work here
| Time est | St. Dev | Variance
a | 12 | 0.33 | 0.1089
b | 7 | 1.1667 | 1.361
c | 17 | 3 | 9
d | 16 | 1.333 | 1.78
e | 13 | 2.5 | 6.25
f | 15 | 2.83 | 8.03
g | 17 | 1 | 1
h | 14 | 1.667 | 2.779
i | 14 | 1.5 | 2.25
j | 14 | 0.67 | 0.44
k | 14 | 2.33 | 5.43
QB: | a | → | e | → | f | → | h | → | j | → | k
QC: |  | ES | EF | LS | LF | Slack | Duration
| a | 0 | 12 | 12 | 24 | 12 | 12
| b | 12 | 19 | 14 | 21 | 2 | 7
| c | 0 | 17 | 4 | 21 | 4 | 17
| d | 19 | 35 | 21 | 37 | 2 | 16
| e | 12 | 25 | 24 | 37 | 12 | 13
| f | 25 | 40 | 25 | 40 | 0 | 15
| g | 35 | 52 | 37 | 54 | 2 | 17
| h | 40 | 54 | 40 | 54 | 0 | 14
| i | 52 | 66 | 54 | 68 | 2 | 14
| j | 54 | 68 | 54 | 68 | 0 | 14
| k | 68 | 82 |  |  | 0 | 14
QD:
| MS | b | c | d | g | i
| LS | a | e | f | h | j | k
QE: | 82
QF: | σ = √VCP |  |  | = | √ | 38.4289 | 5.7
| Z= | （83-82) | /5.7 | ≈ | 0.3
| probability | ： | 0.62

## Q3 Resource Levelling
Scheduled Resource Load Chart with ES and Slack updates
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | 2 | 3 | 0 | 4 | 1 | 2 | 2 | 2 | [17 empty] | 0 | 1 | 3
2 | 1 | 4 | 0 | 4 | 0 | 1 | 1 | 1 | 1 | [16 empty] | 1 | 2
3 | 1 | 5 | 0 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | [15 empty] | 1 | 3 | 4
4 | 1 | 6 | 4 | 10 | 0 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 4 | 4 | 10
5 | 2 | 4 | 5 | 10 | 1 | [5 empty] | 2 | 2 | 2 | 2 | [14 empty] | 0 | 1
6 | 2 | 3 | 10 | 13 | 0 | [10 empty] | 2 | 2 | 2 | [10 empty] | 4 | 6 | 10
Resources Scheduled | [5 empty] | 4 | 4 | 4 | 2 | 2 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 2 | [7 empty] | 0 | 2 | 4 |  |  |  | 10 | 6 | 13
Resources Available | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [5 empty] | 0 | 1 |  |  |  |  | 0 | 2
[26 empty] | 0 | 4 | 4 |  |  |  | 10 | 3 | 13
[8 empty] | repeat the table above repeatedly underneath it, showing each resource levelling step | [20 empty] | 5 | 5 | 9
[29 empty] | 1 | 2
[29 empty] | 6 | 4 | 10
[26 empty] | 0 | 3 | 5 |  |  |  | ES | ID | EF
[26 empty] | 0 | 1 |  |  |  |  | SL | Resource # Required
[26 empty] | 1 | 5 | 6 |  |  |  | LS | DUR | LF
[26 empty] | 0 | 1 | 3
[26 empty] | 3 | 2
[26 empty] | 3 | 3 | 6
[29 empty] | 4 | 4 | 10
[29 empty] | 2 | 1
[29 empty] | 6 | 6 | 12
[26 empty] | 0 | 2 | 4 |  |  |  | 12 | 6 | 15
[26 empty] | 2 | 1 |  |  |  |  | 0 | 2
[26 empty] | 2 | 4 | 6 |  |  |  | 12 | 3 | 15
[29 empty] | 8 | 5 | 12
[29 empty] | 0 | 2
[29 empty] | 8 | 4 | 12
[26 empty] | 3 | 3 | 8 |  |  |  | ES | ID | EF
[26 empty] | 0 | 1 |  |  |  |  | SL | Resource # Required
[26 empty] | 3 | 5 | 8 |  |  |  | LS | DUR | LF
[26 empty] | Period |  | Start | Ongoing |  | Delay
[26 empty] | 0-1 |  | 2(slack 2)
1(slack 3)
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [9 empty] | 3(slack 0)
1 | 2 | 3 | 0 | 6 | 3 | 2 | 2 | 2 | [17 empty] | 1-2 |  |  | 1
2 | 1 | 4 | 0 | 6 | 2 | 1 | 1 | 1 | 1 | [19 empty] | 2
3 | 1 | 5 | 3 | 8 | 0 |  |  |  | 1 | 1 | 1 | 1 | 1 | [17 empty] | 3(slack -1)
4 | 1 | 6 | 4 | 12 | 2 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 2-3 |  |  | 1
5 | 2 | 4 | 8 | 12 | 0 | [8 empty] | 2 | 2 | 2 | 2 | [11 empty] | 2
6 | 2 | 3 | 12 | 15 | 0 | [12 empty] | 2 | 2 | 2 | [10 empty] | 3(slack -2)
Resources REScheduled | [5 empty] | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 3-4 |  | 3
Resources Available | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [8 empty] | 2
[26 empty] | 4-5 |  | 4
3
[26 empty] | 5-6 |  |  | 3
4
5(slack 0)
[26 empty] | 6-7 |  |  | 3
4
5(slack -1)
[26 empty] | 7-8 |  |  | 3
4
5(slack -2)
[26 empty] | 8-9 |  |  | 4
5
4
[26 empty] | 9-10 |  |  | 4
5
[26 empty] | 10-11 |  |  | 5
6(slack -1)
[26 empty] | 11-12 |  |  | 5
6(slack -2)
[26 empty] | 12-13 |  | 6
[26 empty] | 13-14 |  |  | 6
[26 empty] | 14-15 |  |  | 6
[22 empty] | Order: | 2 | 1 | 3 | 4 | 5 | 6
[22 empty] | Critical: | 3 | 5 | 6
[22 empty] | Slack of 1 |  | 3
[22 empty] | Slack of 4 |  | 2
[22 empty] | Slack of 5 |  | 0